| Dy.General Manager (NWP-CFA) O/o PGM(Development) Tamil Nadu Telecom Circle Tamil Nadu Telecom Complex, IV Floor, No.60, Ethiraj Salai, Chennai – 600 008 |  |
| --- | --- |

MINUTES OF MEETING WITH NIC, CHENNAI ON L2 VPN CONNECTIVITY TO UNIVERSITIES

A meeting was held under the chairmanship of Sr. GM (NWP-CFA), Tamilnadu Circle at the conference hall of O/o PGM (CFA), TN Circle, Chennai -8 at 12.00 hrs on 10-10-11 for the implementation of L2 VPN connectivity with NKN POP  to the Universities in Tamilnadu Circle and Chennai Telephones  which are provided with 1 GE connectivity under NMEICT project.

The officers from NIC, Chennai, Chennai Telephones, STR, Chennai and Tamilnadu Circle have participated in the meeting.  The list of officers participated is given in the Annexure.

DGM (NWP-CFA),Tamilnadu Circle  welcomed the participants.

Sr.General Manager (NWP-CFA), Tamilnadu Circle informed  that BSNL CO., ND has given  31-10-2011 as target date for completion of L2 VPN connectivity with NKN POP. Some of the Circles have completed the migration of some universities to their respective NKN POPs  as test cases and on monitoring the performance, they may further migrate other universities in their Circle.

Tamilnadu Circle is having 29 universities and Chennai Telephones with 18 Universities  for migration to NKN POP at Beasant Nagar, Chennai.  He suggested that Central University, Tiruvarur may be taken as a test case for L2 connectivity and to complete for all Universities by the end of this month.

GM (EBII), Chennai Telephones said that before migration, precautions to be taken up for the speed low cases.  Chennai Telephones is ready in all respects for the migration.

Mr. Gopinath, Scientist (D), NIC, Chennai informed that

- they have to send the list of Universities of Tamilnadu Circle and Chennai Telephones to their Headquarters at Delhi and will get approval  for the migration.

- NIC, Chennai  have to supply the routers at the university end and it may not be possible to complete the supply by the end of this month.

- Anna University, Trichy in Tamilnadu Circle and Cresant University in Chennai Telephones may be taken as test cases since the migration will be made easy as their routers are available at these Universities and trained technical personnel are available for co-ordination.

- Bharathidasan university of Tamilnadu Circle may be taken as next University for the migration.

- For the connectivity of test cases, the approval from MHRD is not needed.

- NIT, Trichy is to be treated as Research Centre and 2 GE links can be given,

Mr. Nehru, Technical Director, NIC, Chennai raised the following clarifications:

- As the Universities are to be migrated to NKN POP at NIC, Chennai, the payment policy is to be clarified.

- It is proposed to shift the NIC servers etc. which are in first floor to the second floor of Beasant Nagar building shortly due to inadequate space.

- BSNL has to deploy additional man power through outsourcing for making IP configuration in all the nodes of the universities as most of the end users do not have software trained personnel to handle IP port configuration for migration from NME to NKN.

- Is BSNL  providing the LAN network:

- A BSNL nodal officer is to be made available at office of NIC, Chennai for better co-ordination.

Sr. GM (NWP-CFA) informed that at the university end, no infra equipment was supplied by BSNL and only network connectivity is provided by BSNL. Further he explained that BSNL is the 10% stake holder in NMEICT project and out of balance 90%, MHRD will bear 75%  of the cost and 25% by Universities and the project is for 10 years period.  For LAN provision,  BSNL has floated a tender and shortlisted the vendors .  This LAN project is for a maximum of 400 nodes inside the university campus with one L3 and twenty L2 switches and laying of OF cable for up to 7.5 km inside the campus. M/s Sai Info Systems  Ltd is the approved vendor for South Zone for LAN implementation.  Work orders will be issued by STP, HYD after getting the willingness letters from the Universities concerned. So far SASTRA university, Thanjavur has given their consent letter for LAN implementation.

Sr.GM (CFA-NWP), TN Circle  has raised the point about the timeframe given by BSNL CO., ND for speedy implementation/completion of the Project. He also sought to know the built-up facility at Haddows Road for MPLS routing.  For this, STR has intimated that there won’t be any problem and sufficient ports are available at Haddows Road which can cater to all University connectivity.

DE, STR, Chennai informed that one no. Of 10G 12 channel DWDM system is working between Chennai Nunkambakkam Haddows road, STR DXC to NIC, Beasant Nagar, Chennai.  In this system four nos. of STM 16, one no. of STM 64 are working at present.  11 nos. of 1 GE   and 2 nos. of STM 64 are allotted and are yet to be commissioned.  As per NIC , Chennai, the available bandwidth is sufficient for connecting all the universities of Tamilnadu Circle and Chennai Telephones.  With the continuous monitoring of traffic , NIC, Chennai informed that it is expected that  5 more ports may be required to meet the traffic, for which STR had informed that  sufficient band width is available now and further can be extended at any point of time.

DGM (EB Sales II), Chennai Telephones) has informed that two  GE links from Chennai Haddows Road RPR Switch to NKN POP at NIC, Chennai has already been established and kept ready. It is suggested to take B.S. Abdur Rahman University as next to Cresant University.

Decisions taken:

- NIC, Chennai will configure the extended 2GE ports in NKN POP and ensure connectivity of NKN POP and BSNL POP with 2GE ports.

- Anna University, Trichy in Tamilnadu Circle and Cresent University in Chennai Telephones are to be connected with NIC, Chennai through L2 VPN at the first instance and to be completed at the earliest.

- Based on the quantum of  work involved and experience gained from the test cases,  the rest of the universities of both circles will be taken up.

- The following  officers are nominated as  nodal officers for the implementation of L2 VPN connectivity to all universities .

- G. Rama 	   AGM (BBV)               -   Tamilnadu Circle

- V. Lakshmi   AGM (Sales EB II)    -   Chennai Telephones

- S. Gopinath  Scientist (D)	          -   NIC Chennai

The Meeting concluded with a vote of thanks by AGM (BB-VAS), TN Circle.

Endt No. BB/COLLEGES/2011-12/VOL.  I/Part I/26 dt. 17-10-2011

Sd/-

Encl:  as above.

Dy. General Manager (NWP-CFA)

For  Pr.General Manager (Dev.)

BSNL, T.N Circle, Chennai-8

Copy To:-

- Sr. General Manager (BB), BSNL, Corporate Office, New Delhi.

- Sr. General Manager (STP), Hyderabad

- CGM Chennai Telephones, Chennai

- All participants.

LIST OF PARTICIPANTS

| S.NO. | NAME | DESIGNATION | UNIT | PHONE NO. | MOBILE NUMBER | E-MAIL ID |
| --- | --- | --- | --- | --- | --- | --- |
|  | Shri/Smt |  |  |  |  |  |
| 1 | P. JAGADEESAN | SR.GM(NWP-CFA) | TN CIRCLE,CHI-8 | 28265559 | 9444000912 | pjagadeesan5358@yahoo.com |
| 2 | V. SOMASUNDARAM | G.M. (EB-II) | CHTD |  | 9445262888 | gmeb2chn@gmail.com |
| 3 | M. THIRUNAVUKKARASU | DGM (NWP-CFA) | TN CIRCLE, CHI-8 |  | 28262940 | tarasu6@rediffmail.com |
| 4 | S. MADHUSUDHANAN | DGM (EB-II SALES) | CHTD | 26478447 | 9444977979 | smadhusudhanan@bsnl.co.in |
| 5 | E. ENIYA NEHRU | SR. TECHNICIAL DIRECTOR | NIC,CHI | 24902580 | 9444411664 | nehru@nic.in |
| 6 | S. GOPINATH | SCIENTIST (D) | NIC,CHI | 24917850 | 9380241430 | sgopinath@nic.in |
| 7 | N. SURYAMURTHY | DE STR | CHI | 25363269 | 9486106590 | suryabsnl46@gmail.com |
| 8 | J. RAVI | DE NIB | CHTD | 28204646 | 9444038593 | ajravi@dataone.in |
| 9 | V. LAKSHMI | AGM (SALES)EB II | CHTD | 26478405 | 9445399900 | lakshmiv@bsnl.co.in |
| 10 | LAKSHMI RAMACHANDRAN | SDE (BB-INSTLN) | CHTD | 28280055 | 9444979664 | lakshmir@bsnl.co.in |
| 11 | G. RAMA | AGM (BB-VAS) | TN CIRCLE, CHI-8 | 28312232 | 9443100838 | ramapichi@gmail.com |